## Sheet2
Notes | Date | Activity - INTERNAL | Activity/notes - EXTERNAL | People involved | Venue | Actions
WC | 2 months approx prior to recruitment | Initial discussion Trustee roles/ review of skills | agreed with Chair/ Board to action skills profile required | Board | Teams
WC |  | Role descriptor & person spec reviewed & agreed |  | Lead ; Chair & CEO
WC | 1 month prior to start of campaign | Initial campaign meeting with Lead & administrator to discuss vacancy | All tracking and Applicant resposes by CCF. Stats requred through campaign | Lead & Ad | Teams call
WC |  | Campaign Plan produced with provisional dates |  | Lead & Ad
WC |  | Plan External Search | - On line advert & online media/sources to be agreed.Try to use as many contacts as possible including charities and Impact groups VPs .100 Club . Donors .Reach Vounteering, Indeed, LinkedIn etc | Lead & Admin
WC | 2/3 weeks prior to advertising | Advert written & Complete | Review by Lead Chair CEO | Lead CEO Chair
WC |  | Assessment process to be agreed for Assignment pack- CV & covering letter from applicants | Assessors agreed for shortlisting/initial discussions/ panel interviews. | Lead CEO Chair | email teams?
W/C |  | Agree dates: closing dates, screening, shortlisting, briefings, interviews as below | Advertise for 6 or 7 weeks - closing date xx | Lead Ad
W/C |  | Confirm availability dates | Confirm with assessors : Trustees discussion longlist / shortlisting/ interviews | Lead Ad
W/C |  | Assignment Pack written and agreed update material provided |  | CEO Lead Chair Ad
W/C |  | Remind assessors of involvement and provide CCF Recruitment Policy | Prior to interviews | lead | email
W/C | min 6/7 weeks prior to shortlisting | Vacancy advertised with closing date | Posted with infrastructure orgs, CCF social media, website + inclusion in newsletter etc | admin
W/C |  | Search email written. Search known friends , VP, colleagues agreed as above | Search discussions/emails commence following Board meeting to discuss/ confirm approach. | CEO Chair
W/C |  | Briefs Advert and info sent to trustees |  | lead | email
WC | Prior to close date | Agree screening criteria | use RDs & PS . Produce a screening check list | Lead Adm
WC | tba | weekly update TC |  | Lead & ad
W/C |  |  | Closing date for return of external applications | Admin
| Prior to shortlisting date | Applications sent to panel members | External application screening- All candidates using checklist | Admin
W/C |  | Briefing note & agenda for shortlisting meeting | agenda & attachments required | Lead | email
W/C | min 2 weeks prior to ints | Application Screening. Review applications received and agree next steps | Proposed - initial screening as interview panel | Panel | Teams/ calls or email if Req.
|  | Trustees-Meeting to discuss short list . | All applicant documentation required for panels- , criteria. candidate profiles and letters.Role descriptor Agenda | Lead & Panel
WC | Pre Ints | Agree and produce interview plan |  | Lead
WC |  | Agree and produce interview questions and competency matrix required | Do we need to consult re specialist knowledge | Lead Ad
W/C |  | Admin. | All external candidates acknowledged by letter giving prov int dates etc . List of candidates produced for screening | Ad
|  | Briefing note & Agenda for panel members re Interviews | Docs:, Recruitment & selection Policy , Int Guidelines , Questions & ratings matrix. Interview timings . Agenda | Lead &Ad | Email
| Min 2 weeks Prior | Briefing Meeting with Panel members |  | All involved | Mtg/teams
W/C |  | Assessor packs prepared & issued for panel Interviews. | CV, covering letters. Int docs etc Briefing meeting has to have been held | MC all admin. Consult DB
W/C |  | invitations issued to candidates assessment/interview | Invitations issued to assessment /interview | Ad | Book mtgs
W/C |  | Planning for interviews by assessors | Read applications & prepare | All involved
W/C |  | Conduct assessment/interviews . Review of candidates | Over 2 weeks for availability ( 4 on Panel ) | lead & panel
W/C |  | Verbal references obtained | if necessary | Ad
W/E | After Ints | Telephone & Process successful candidates. |  | Ad
W/C | After ints | Telephone unsuccesful candidates | Telephone/send letters. unsuccessful candidates | Lead
W/C |  | Agree next steps & letter of engagement and send |  | Chair CEO
W/C |  | Plan intro dates & send relevant information |  | CEO ad
W/C |  | Successful potential candidate invited to meet the Board |  | Chair CEO
W/C |  | Review Process & success | Check Diversity Questionnairre | All involved
|  | After attending events etc Formal offer & Induction |  | Chair CEO